## Backlog
Guest House Ops Hub — Product Backlog v1.0
Source: discovery doc 14 (14-backlog.md). Delta-to-enterprise-quality; delivered baseline excluded. Cross-refs: doc 02 (FR/NFR), 05 (BR), 06 (GAP), 07 (RSK), 09 (Q).
Epic | Epic name | Story ID | As a… | Story | Acceptance criteria (Given/When/Then) | References | Priority | Points | Status
E1 | Production Safety & Operability | US-101 | MindBit ops | Automated daily backups with an offsite copy per client DB | GIVEN a client deployment WHEN the nightly job runs THEN a restorable snapshot exists offsite, retention 30d, and failure alerts ops. | GAP-1, RSK-08 | P0 | 5 | Proposed
E1 | Production Safety & Operability | US-102 | MindBit ops | Documented, drilled restore runbook | GIVEN a snapshot WHEN the runbook is executed on a scratch instance quarterly THEN RTO ≤ 4h is verified and logged. | GAP-1 | P0 | 3 | Proposed
E1 | Production Safety & Operability | US-103 | MindBit ops | Error tracking + uptime checks on every deployment | GIVEN an unhandled error or downtime WHEN it occurs THEN it appears in monitoring within 5 min tagged by client, and the UI shows an incident ID. | GAP-17 | P0 | 5 | Proposed
E1 | Production Safety & Operability | US-104 | Owner | Sync health visible (iCal last-success, forwarder heartbeat, cron status) with staleness warnings | GIVEN a feed not synced >12h WHEN I open Feeds/Today THEN a visible warning shows the age AND a push/alert fires (with E5). | GAP-5, BR-AVL-05 | P0 | 5 | Proposed
E1 | Production Safety & Operability | US-105 | MindBit ops | Fleet dashboard: version, health, cron, backup status across clients | GIVEN ≥2 deployments WHEN I open the dashboard THEN each shows version+health+last backup+last sync, red on breach. | GAP-18 | P1 | 8 | Proposed
E2 | Compliance: DPDP, Form C, GST | US-201 | Owner | Pre-filled Form C artefact for a foreign guest, with submission tracking | GIVEN a checked-in foreign guest WHEN I tap 'Form C' THEN a print-ready artefact with the 13 fields renders; a due-in-24h reminder persists until 'submitted' is ticked (audited). | GAP-7, Q-LEG-02 | P0 | 5 | Proposed
E2 | Compliance: DPDP, Form C, GST | US-202 | Owner | Export and erase all data held about a guest (DPDP rights) | GIVEN a guest requests erasure WHEN I trigger it THEN PII is removed/anonymised, bookings keep non-identifying financial integrity, and the action is audited. | GAP-8 | P0 | 8 | Proposed
E2 | Compliance: DPDP, Form C, GST | US-203 | MindBit | Sane ID-scan retention default; purge provably runs | GIVEN a new property WHEN created THEN idRetentionDays defaults (e.g. 180); purge logs deletions; owner notified of policy. | BR-GST-05 | P0 | 3 | Proposed
E2 | Compliance: DPDP, Form C, GST | US-204 | MindBit | Breach-notification runbook + guest-facing privacy notice (incl. AI/US-cloud processing) | Docs approved by counsel; notice linked in app. | NFR-PRV-01/04 | P0 | 3 | Proposed
E2 | Compliance: DPDP, Form C, GST | US-205 | Owner (GST) | Invoices carry sequential per-FY numbers, GST lines, stored immutably | GIVEN GSTIN configured WHEN an invoice is issued THEN an Invoice record exists with number series, tax lines per rate, immutable snapshot; reprint is identical. | GAP-11, Q-FIN-02 | P1 | 8 | Proposed
E2 | Compliance: DPDP, Form C, GST | US-206 | Guest | Server-side PDF invoices | Pixel-stable PDF, downloadable on a phone. | GAP-11 | P2 | 5 | Proposed
E3 | OTA Ingestion completeness | US-301 | Reception | OTA modification/cancellation emails match the existing booking and guide the update | GIVEN a booking with otaRef X WHEN a modification email for X is ingested THEN the pending item links to the booking, shows a diff, and 'Apply' updates via the normal conflict-checked path. | GAP-2 | P0 | 8 | Proposed
E3 | OTA Ingestion completeness | US-302 | MindBit | Fixture corpus of real OTA emails gates parser changes in CI | GIVEN the corpus (Q-OTA-02) WHEN the parser changes THEN CI runs fixtures and reports extraction accuracy. | RSK-13 | P1 | 5 | Proposed
E3 | OTA Ingestion completeness | US-303 | Owner | Configurable iCal sync frequency (up to hourly) | Configurable; respects OTA politeness; health surfaced (US-104). | GAP-6 | P2 | 3 | Proposed
E3 | OTA Ingestion completeness | US-304 | Owner | Last-room oversell buffer per room type | GIVEN buffer=1 on Deluxe(3 units) WHEN 2 are booked THEN agent/community availability reports 0; direct booking still possible with warning. | GAP-24 | P2 | 5 | Proposed
E3 | OTA Ingestion completeness | US-305 | Reception | Duplicate OTA confirmations never create two bookings | GIVEN a booking with otaRef X WHEN the same-ref email is ingested THEN it is flagged duplicate; no new pending create. | BR-OTA-03 | P1 | 3 | Proposed
E3 | OTA Ingestion completeness | US-306 | MindBit | Card data redacted from ingested emails before storage | GIVEN a fixture containing a virtual card WHEN ingested THEN the stored record contains none of it. | ASM-18, Q-OTA-03 | P1 | 2 | Proposed
E4 | Money correctness | US-401 | Engineering | Money as integer paise end-to-end with a typed money util | All money fields migrated; property tests on arithmetic; CSVs/invoices unchanged to the rupee. | GAP-9 | P0 | 8 | Proposed
E4 | Money correctness | US-402 | Owner | Staff API responses never contain money fields | GIVEN a reception session WHEN any endpoint returns a reservation THEN grossAmount etc. are absent; contract tests per role. | GAP-12 | P0 | 5 | Proposed
E4 | Money correctness | US-403 | Engineering | Postgres RLS enforces property scoping (defence-in-depth) | RLS policies on tenant tables keyed to session property; raw-SQL leak test proves containment. | GAP-12, RSK-17 | P1 | 8 | Proposed
E4 | Money correctness | US-404 | Owner | Payment corrections are void+reversal with audit | Edit disabled; void creates a reversing entry; both audited. | BR-PAY-05, Q-FIN-04 | P1 | 3 | Proposed
E4 | Money correctness | US-405 | Owner | OTA payout recording with owed-vs-received per OTA | Payout entity matched to bookings; Finance shows variance. | GAP-13 | P2 | 5 | Proposed
E4 | Money correctness | US-406 | Owner | Deterministic refund rules per ratified answers | Ladder base per Q-FIN-07; refund ≤ paid enforced; OTA-collect path documented. | BR-CANC-03/04/05 | P1 | 3 | Proposed
E4 | Money correctness | US-407 | Owner | Razorpay capture + room-hold (when keys provided) | Idempotent webhook (replay-safe test); hold expires → release; exclusion constraint untouched. | FR-PAY-5 | P1 | 8 | Proposed
E5 | Notifications & Messaging activation | US-501 | Owner | Push notification for high-severity escalations and new conflicts | GIVEN a subscribed device WHEN the event fires THEN push within 1 min, deep-linking to the item; per-event toggles in Settings. | GAP-14, BR-AI-05 | P0 | 5 | Proposed
E5 | Notifications & Messaging activation | US-502 | MindBit | WhatsApp templates (En/Kha/Hi) approved and parameterised | Templates submitted+approved; outbox sends real messages with params; language chosen per guest. | GAP-3 | P1 | 8 | Proposed
E5 | Notifications & Messaging activation | US-503 | Owner | Guest replies visible in a unified message log | Inbound webhook stores replies; thread view per guest; ownership per Q-AI-04 decision. | GAP-4 | P2 | 5 | Proposed
E5 | Notifications & Messaging activation | US-504 | Guest | Message opt-out and quiet hours | STOP handling; no sends 22:00–07:00 except OTP-class. | RSK-15 | P1 | 3 | Proposed
E6 | Auth & access hardening | US-601 | Staff | Join via email invite and set own password | Invite → expiring link → set password → role/property pre-assigned. | GAP-10 | P0 | 5 | Proposed
E6 | Auth & access hardening | US-602 | Any user | Self-service password reset | Reset link, single-use, rate-limited. | GAP-10 | P0 | 3 | Proposed
E6 | Auth & access hardening | US-603 | Owner | Disable/role change revokes sessions | Per Q-SEC-03 ratified semantics; test proves stale session rejected. | AMB-21 | P1 | 3 | Proposed
E6 | Auth & access hardening | US-604 | Owner | ID-document access is logged | Every view/download → audit entry; owner-visible. | Q-SEC-04, GAP-15 | P1 | 2 | Proposed
E6 | Auth & access hardening | US-605 | Engineering | Keyed hashing for shared-list phone matching | Pepper per network; enumeration infeasible; migration for existing hashes. | NFR-SEC-09 | P1 | 3 | Proposed
E6 | Auth & access hardening | US-606 | Engineering | CI guard for raw-SQL tenant scoping | Lint rule / grep-gate fails PRs with unscoped tenant-table raw SQL. | NFR-SEC-06 | P1 | 2 | Proposed
E7 | Fleet & onboarding | US-701 | MindBit ops | One-command client provisioning (deploy+DB+seed+env) | New deployment live <2h hands-on; checklist auto-verified. | GAP-18, Q-DEP-01 | P1 | 8 | Proposed
E7 | Fleet & onboarding | US-702 | New owner | Setup wizard: property, rooms, channels, policies, staff | First-run wizard completes to a bookable state without support. | GAP-18 | P1 | 8 | Proposed
E7 | Fleet & onboarding | US-703 | MindBit ops | Staged fleet upgrades (canary → all) with pre-migration backup gates | Scripted; halt-on-failure; version visible in fleet dashboard. | RSK-09 | P1 | 5 | Proposed
E7 | Fleet & onboarding | US-704 | Client | Complete data export on request (offboarding) | DB export + documents + CSVs delivered; runbook. | GAP-23 | P2 | 3 | Proposed
E7 | Fleet & onboarding | US-705 | MindBit | Pilot billing operates with a rate card | Pricing ratified (Q-BUS-03); invoices issued; revenue tracked vs grant milestone. | GAP-27 | P1 | 2 | Proposed
E7 | Fleet & onboarding | US-706 | Sales | Seeded demo tenant | Demo data realistic; reset script. | GAP-30 | P2 | 2 | Proposed
E8 | Localization & accessibility | US-801 | Engineering | All UI strings externalized (i18n framework) | No hardcoded user-facing strings; language-switch scaffolding. | GAP-16 | P1 | 8 | Proposed
E8 | Localization & accessibility | US-802 | Khasi-speaking operator | Core flows available in Khasi | Today/Calendar/Booking/Payments/Housekeeping translated; reviewed per Q-L10N-03. | GAP-16 | P2 | 8 | Proposed
E8 | Localization & accessibility | US-803 | Any user | Core flows meet WCAG 2.1 AA basics | Contrast, touch targets ≥44px, labels; audit checklist passes. | GAP-21 | P2 | 5 | Proposed
E9 | Verification & spec-truth | US-901 | Team | Offline behaviour audited and specified honestly | Doc: which reads cache, which writes queue, conflict UX; User Guide corrected if overstated; 2G field test. | GAP-25, Q-TEC-04 | P0 | 5 | Proposed
E9 | Verification & spec-truth | US-902 | Team | Community topology documented as an ADR | Where registries live, who controls, failure modes; counsel-reviewed. | GAP-26, Q-LEG-03 | P0 | 3 | Proposed
E9 | Verification & spec-truth | US-903 | Engineering | Route-level test: booking create overlap → 409 | Vitest route test green; guards db-errors sniffing. | NFR-MNT-02 | P0 | 2 | Proposed
E9 | Verification & spec-truth | US-904 | Engineering | Housekeeping derivation test | Checkout ⇒ task appears; mark-clean ⇒ ready. | NFR-MNT-02 | P1 | 2 | Proposed
E9 | Verification & spec-truth | US-905 | Team | Room-assignment product stance ratified and recorded | Decision workshop output; if type-level chosen, spike estimates constraint redesign. | GAP-29, Q-OPS-05 | P1 | 2 | Proposed
E9 | Verification & spec-truth | US-906 | Engineering | Per-feed iCal tokens replace the single token | Rotation per feed; old URLs invalidated gracefully. | ROADMAP suggestion | P2 | 3 | Proposed
E9 | Verification & spec-truth | US-907 | Engineering | Guest merge tool with audit | Merge preserves stays/LTV; irreversible warning; audited. | GAP-19 | P2 | 5 | Proposed

## Epic Summary
Epic Summary — counts & points derive from the Backlog sheet
Epic | Epic name | Stories | Points | P0 stories | P1 stories | P2 stories | P0 points
E1 | Production Safety & Operability | 5 | 26 | 4 | 1 | 0 | 18
E2 | Compliance: DPDP, Form C, GST | 6 | 32 | 4 | 1 | 1 | 19
E3 | OTA Ingestion completeness | 6 | 26 | 1 | 3 | 2 | 8
E4 | Money correctness | 7 | 40 | 2 | 4 | 1 | 13
E5 | Notifications & Messaging activation | 4 | 21 | 1 | 2 | 1 | 5
E6 | Auth & access hardening | 6 | 18 | 2 | 4 | 0 | 8
E7 | Fleet & onboarding | 6 | 28 | 0 | 4 | 2 | 0
E8 | Localization & accessibility | 3 | 21 | 0 | 1 | 2 | 0
E9 | Verification & spec-truth | 7 | 22 | 3 | 2 | 2 | 10
| TOTAL | 50 | 234 | 17 | 22 | 11 | 81

## DoR · DoD · Legend
Working agreements
Definition of Ready | Open questions referenced by the story are answered; acceptance criteria agreed; test data identified; any touch to the GiST-constraint/migration machinery flagged for senior review.
Definition of Done | Code + tests (unit; route-level where API changes) green in CI; migration via db:migrate:new only; docs updated (USER-GUIDE/ARCHITECTURE); audit/RBAC respected; deployed to a pilot-mirror environment; demoed.
Priority P0 | Production-safety / legal — gate for scaling past first pilots (Roadmap Phase 1).
Priority P1 | Scale & commercial — grant Q2/Q3 alignment (Roadmap Phase 2).
Priority P2 | Quality & experience — Roadmap Phase 3.
Status values | Proposed → Ready → In progress → Done (set 'Proposed' by default; update during grooming).
Import note | Backlog sheet columns map 1:1 to Jira CSV import (Epic Link, Summary=Story, Description=AC, Labels=References, Priority, Story Points).